## Sheet1
Group | Parts | Needed | Have | Still Needed | Order From | Payment | PR #
Sensors | PAR Sensors | 10 | 10 | 0
| Pressure Sensors-100m | 10 | 10 | 0
| Pressure Sensors-30m | 10 | 10 | 0
| Thermistor Plugs | 8 | 8 | 0
| Vacuum Ports | 10 | 0 | 10 | McMaster | UW | 4 | http://www.mcmaster.com/#51605k29/=12omluf
Mechanical | 12" Trawl Floats | 8 | 2 | 6 | Seamar | Credit Card
| Burn Wire Releases | 11 | 3 | 8 | Sub Sea Sonics | UW | 5 | http://subseasonics.com/underwater-timed-release-tr-45_prices/
| Burn Wire Release Links | 10 | 0 | 10 | Sub Sea Sonics | UW | 5 | http://subseasonics.com/underwater-timed-release-tr-45_prices/
| End Cap Piston O Rings | 10 | 0 | 10 | McMaster | UW | 4
| End Cap Face O Rings | 10 | 0 | 10 | McMaster | UW | 4
| PAR O Rings | 20 | 0 | 10 | McMaster | UW | 4
| Pressure/Vacuum O Rings | 30 | 0 | 10 | McMaster | UW | 4
| End Caps | 8 | 0 | 8 | Shop
| PAR Housings | 8 | 0 | 8 | Shop
| Pressure Sensor Housings | 16 | 0 | 16 | Shop
| Vacuum Port Caps | 8 | 0 | 8 | Shop
| PCB Frames | 8 | 0 | 8 | Shop
| Release Frames | 8 | 0 | 8 | Shop
| Burn Wire Mount Arms | 16 | 0 | 16 | Shop
| Release Arms | 8 | 0 | 8 | Shop
| Burn Wire Clamps | 8 | 0 | 8
Electronics | PCBs | 8 | 2 | 6 | PCBA Express | Credit Card
| PCB Components | 8 | 2 | 8 | Digikey | UW
| Arduino Megas | 8 | 0 | 8 | Adafruit | UW | 1
| GPS Chips | 8 | 2 | 8 | Adafruit | UW | 1 | https://www.adafruit.com/products/790
| PCB Assemblies | 8 | 2 | 8 | Schippers | UW
| GPS Antennas | 8 | 1 | 8 | Adafruit | UW | 1 | https://www.adafruit.com/products/960
| Iridium Antennas | 8 | 1 | 7 | Rock 7 | UW | 2 | https://www.rock7mobile.com/shop-product-detail?productId=20
| RockBlocks | 8 | 1 | 7 | Sparkfun | UW | 3 | https://www.sparkfun.com/products/13745
| Battery Packs | 8 | 1 | 7
Assembly | Arctic Alumina | 5 | 2 | 3 | Amazon | Credit Card |  | https://www.amazon.com/Arctic-Silver-Alumina-Adhesive-AATA-5G/dp/B0087X725S/ref=sr_1_1?ie=UTF8&qid=1466698376&sr=8-1&keywords=arctic+alumina
| Syringes | 10 | 0 | 0 | Amazon | Credit Card |  | https://www.amazon.com/10-Pack-Syringe-Tipped-Storage/dp/B01D6D3Y14/ref=sr_1_17?ie=UTF8&qid=1466698276&sr=8-17-spons&keywords=syringe+14+ga&psc=1
| Cap Screws for PCB Frame | 20 | 0 | 20 | McMaster | UW | 4
| Hardware: Float to Frame | 8 | 0 | 8 | McMaster | UW
| Mooring Hardware | 8 | 0 | 8 | McMaster | UW
| Anchors | 6 | 0 | 6 | Shop
| Lead Weights | 6 | 0 | 6 | Shop
0
0
0
0
0

## To Calvin
Parts | Qty | Cost | Order From | PR #
GPS Chips | 10 | 239.6 | Adafruit | 1
GPS Antennas | 7 | 90.65 | Adafruit | 1
Arduino Megas | 7 | 349.65 | Adafruit | 1
TOTAL |  | 679.9
Iridium Antennas | 7 | 595 | Rock 7 | 2
TOTAL |  | 595
RockBlocks | 7 | 1749.65 | Sparkfun | 3
TOTAL |  | 1749.65
Vacuum Ports | 10 | 103.8 | McMaster | 4
TOTAL |  | 103.8
Burn Wire Releases | 8 | 1320 | Sub Sea Sonics | 5
Burn Wire Release Links | 10 | 40 | Sub Sea Sonics | 5
TOTAL |  | 1360
Electronics Components | 10 | 1045.81 | Digikey | 6
TOTAL |  | 1045.81
GRAND TOTAL |  | 5534.16
Battery Packs | 8
Burn Wire Clamps | 8
PCB Components | 8 |  | Digikey
PCB Assemblies | 8 |  | Schippers
Hardware: Float to Frame | 8 |  | McMaster
Mooring Hardware | 8 |  | McMaster
12" Trawl Floats | 8 |  | Seamar
PCBs | 8 |  | PCBA Express
End Caps | 8 |  | Shop
PAR Housings | 8 |  | Shop
Pressure Sensor Housings | 16 |  | Shop
Vacuum Port Caps | 8 |  | Shop
PCB Frames | 8 |  | Shop
Release Frames | 8 |  | Shop
Burn Wire Mount Arms | 16 |  | Shop
Release Arms | 8 |  | Shop
Anchors | 6 |  | Shop
Lead Weights | 6 |  | Shop